## Sheet1
﻿
| Project Name | Su Integration
| Document Name | Su Certification
| PMS Name | SaitoShoji Co
| Ref. Document | Su API Document
Analysed By
Date of Analyse
Module Name | Property Creation
Analysed By
Date of Analyse
Test Case Id | Test Scenario | Test Case | Pre-Condition | Test Steps | Expected Result | Error / Post Condition | Actual Result | Status (Pass/Fail)
Case # 1 | Creating Property | Existing / Duplicated Hotel Id | Need to place New Holel ID with mandatory Details | Need to place New Holel ID with mandatory Details | Property already exists / Duplicated | { "Status": "Fail", "Errors": { "ShortText": "Property already exists" } } | {"Status":"Fail","Errors":[{"Code":"547","ShortText":"The property creation limit has been reached. Only 5 properties are allowed to be created."}]} | Pass
Case # 1_1 | Creating Property | Missing any of mandatory Field | Need to place all mandatory filed: Hotel Name, Hotel Code & Currency Code | Need to place all mandatory filed | Bad Request | { "Errors": [ { "Code": "895", "ShortText": "CurrencyCode: Property content is required" } ], "Status": "Fail" } | {"Status":"Fail","Errors":[{"Code":"547","ShortText":"The property creation limit has been reached. Only 5 properties are allowed to be created."}]} | Pass
Case # 1_2 | Creating Property | New Hotel Id with all required fields | Need to place New Holel ID with all mandatory Details | Need to place New Holel ID with mandatory Details | Success | { "Status": "Success" } | {"Status":"Fail","Errors":[{"Code":"547","ShortText":"The property creation limit has been reached. Only 5 properties are allowed to be created."}]} | Fail
Module Name | Room Type Creation
Analysed By
Date of Analyse
Test Case Id | Test Scenario | Test Case | Pre-Condition | Test Steps | Expected Result | Error / Post Condition | Actual Result | Status (Pass/Fail)
Case # 2 | Creating Room Type | Invalid Hotel Id | Need Valid Hotel Id | Place Valid Hotel Id & Room Type Id | Invalid Hotel Code | { "Errors": [ { "Code": "400", "ShortText": "Invalid HotelCode (XYZ)" } ], "Status": "Fail" } | {"Errors":[{"Code":"400","ShortText":"HotelCode: Invalid HotelCode (XYZ)"}],"Status":"Fail"} | Pass
Case # 2_1 | Creating Room Type | Existing / Duplicated Room Type Id | Need Valid Hotel Id& Room Type Id | Place Valid Hotel Id & Room Type Id | Duplicated Room Type | { "Status": "Fail", "Errors": { "Type": "10", "Code": "123444", "ShortText": "Room Already Exist" } } | {"Status":"Fail","Errors":{"Type":"10","Code":"RT003100","ShortText":"Room Already Exists"}} | Pass
Case # 2_2 | Missing Field | Missing any of mandatory Field (Example: Description of room type not placed (Empty node request) - a mandetory field) | Need to place all mandatory filed | Need to place all mandatory filed | Field/s Missing | { "Errors": [{ "Code": "895", "ShortText": "SellableProduct [0]: Property GuestRoom is required" }], "Status": "Fail" } | {"Errors":[{"Code":"900","ShortText":"InvStatusType: Value should be Initial with no InvNotifType, found "}],"Status":"Fail"} | Pass
Case # 2_3 | Creating Room Type | Valid hotel id, Room Type id and details | Need Valid Hotel Id& Room Type Id | Place Valid Hotel Id & Room Type Id | Success | { "Status": "Success" } | { "Status": "Success" } | Pass
Module Name | Deactivating / Activating Room Type
Analysed By
Date of Analyse
Test Case Id | Test Scenario | Test Case | Pre-Condition | Test Steps | Expected Result | Error / Post Condition | Actual Result | Status (Pass/Fail)
Case # 3 | Deactivate Room Type | Invalid Hotel Id | Need Valid Hotel Id | Place Valid Hotel Id | Invalid Hotel Code | { "Errors": [{ "Code": "400", "ShortText": "Invalid HotelCode (XYZ)" }], "Status": "Fail" } | {"Errors":[{"Code":"400","ShortText":"HotelCode: Invalid HotelCode (XYZ)"}],"Status":"Fail"} | Pass
Case # 3_1 | Deactivate Room Type | Invalid Room Type Id | Need Valid Hotel Id& Room Type Id | Place Valid Hotel Id & Room Type Id | Duplicate Room Type Id | { "Status": "Fail", "Errors": { "Type": "10", "Code": 897, "ShortText": "Room Does Not Exist" } } | {"Status":"Fail","Errors":{"Type":"10","Code":null,"ShortText":"Room does not Exists"}} | Pass
Case # 3_2 | Deactivate Room Type | Valid Hotel Id & Room Type Id | Need Valid Hotel Id | Place Valid Hotel Id | Success | { "Status": "Success" } | { "Status": "Success" } | Pass
Module Name | Rate Plan Creation
Analysed By
Date of Analyse
Test Case Id | Test Scenario | Test Case | Pre-Condition | Test Steps | Expected Result | Error / Post Condition | Actual Result | Status (Pass/Fail)
Case # 4 | Creating Rate Plan | Invalid Hotel Id | Need Valid Hotel Id | Place Valid Hotel Id | Invalid Hotel Id | { "Errors": [{ "Code": "400", "ShortText": "Invalid HotelCode (KC5)" }], "Status": "Fail" } | {"Errors":[{"Code":"400","ShortText":"HotelCode: Invalid HotelCode (KC5)"}],"Status":"Fail"} | Pass
Case # 4_1 | Creating Rate Plan | Existing / Duplicated Rate Plan Id | Need Valid Hotel Id& Rate Type Id | Place Valid Hotel Id & Rate Plan Id | Exsiting Rate Plan Id/ Duplicated | { "Errors": [{ "Code": "896", "ShortText": "Requested rate does not qualify. Rate with id 'BAR' already exists" }], "Status": "Fail" } | {"Errors":[{"Code":"896","ShortText":"Requested rate does not qualify. Rate with id RP003113 already exists"}],"Status":"Fail"} | Pass
Case # 4_2 | Missing Field | Missing any of mandatory Field | Need to place all mandatory fileds | Need to place all mandatory filed | Fields Missing | {"Errors":[{"Code":"902","ShortText":"RatePlan [0]: Property Description content is required"}],"Status":"Fail"} | {"Errors":[{"Code":"902","ShortText":"OTA_HotelRatePlanNotifRQ: Description content is required"}],"Status":"Fail"} | Pass
Case # 4_3 | Creating Rate Plan | Valid hotel Id, Rate Plan id and details | Need Valid Hotel Id& Rate Type Id | Place Valid Hotel Id & Rate Plan Id | Success | { "Status": "Success" } | { "Status": "Success" } | Pass
Module Name | Change of Rate Plan Name
Analysed By
Date of Analyse
Test Case Id | Test Scenario | Test Case | Pre-Condition | Test Steps | Expected Result | Error / Post Condition | Actual Result | Status (Pass/Fail)
Case # 5 | Change Rate Plan Name | Invalid Hotel Id | Need Valid Hotel Id | Place Valid Hotel Id | Invalid Hotel Code | { "Errors": [{ "Code": "400", "ShortText": "Invalid HotelCode (KC5)" }, { "Code": "897", "ShortText": "Authorization error. Access denied while trying to update rate 12345889Ab" }], "Status": "Fail" } | {"Errors":[{"Code":"400","ShortText":"HotelCode: Invalid HotelCode (KC5)"}],"Status":"Fail"} | Pass
Case # 5_1 | Change Rate Plan Name | Invalid Rate Plan Id | Need Valid Hotel Id& Rate Type Id | Place Valid Hotel Id & Rate Type Id | Invalid Rate Plan Id | {"Errors":[{"Code":"897","ShortText":"Authorization error. Access denied while trying to update rate 12345889Ab"}],"Status":"Fail"} | {"Errors":[{"Code":"1072","ShortText":"Requested rate does not qualify. Rate with id 999999 not exists"}],"Status":"Fail"} | Pass
Case # 5_2 | Change Rate Plan Name | Valid hotel id and Rate Plan Id | Need Valid Hotel Id& Rate Type Id | Place Valid Hotel Id & Rate Type Id | Success | { "Status": "Success" } | { "Status": "Success" } | Pass
Module Name | Deactivating / Activating Rate Plan
Analysed By
Date of Analyse
Test Case Id | Test Scenario | Test Case | Pre-Condition | Test Steps | Expected Result | Error / Post Condition | Actual Result | Status (Pass/Fail)
Case # 6 | Deactivate / Activate Rate Plan | Invalid Hotel Id | Need Valid Hotel Id | Place Valid Hotel Id | Invalid Hotel Id | { "Errors": [{ "Code": "400", "ShortText": "Invalid HotelCode (KC5)" }, { "Code": "897", "ShortText": "Authorization error. Access denied while trying to update rate BAR" }], "Status": "Fail" } | {"Errors":[{"Code":"400","ShortText":"HotelCode: Invalid HotelCode (KC5)"}],"Status":"Fail"} | Pass
Case # 6_1 | Deactivate / Activate Rate Plan | Invalid Rate Plan Id | Need Valid Hotel Id& Rate Type Id | Place Valid Hotel Id & Rate Type Id | InvalidRate Plan Id | { "Errors": [{ "Code": "897", "ShortText": "Authorization error. Access denied while trying to update rate BAR2" }], "Status": "Fail" } | {"Errors":[{"Code":"1072","ShortText":"Requested rate does not qualify. Rate with id BAR2 not exists"}],"Status":"Fail"} | Pass
Case # 6_2 | Deactivate / Activate Rate Plan | Valid Hotel Id and Rate Plan Id | Need Valid Hotel Id& Rate Type Id | Place Valid Hotel Id & Rate Type Id | Success | { "Status": "Success" } | { "Status": "Success" } | Pass
Module Name | Availability (Rates & Inventory)
Analysed By
Date of Analyse
Test Case Id | Test Scenario | Test Case | Pre-Condition | Test Steps | Expected Result | Error / Post Condition | Actual Result | Status (Pass/Fail)
Case # 7 | Pushing Inventory & Rates | RoomType Id - not existed for Property | Need Valid Hotel Id & Room Type Id | Room Type will be created with availability | Room Type Created on FLY | { "Status": "Sucess" } | { "Success": "Success", "TicketId": "176970429769774894346" } | Pass
Case # 7_1 | Pushing Inventory & Rates | Rate Plan Id - not existed for Property | Need Valid Hotel Id, Room Type Id & Rate Plan Id | Rate Plan will be created with availability | Rate Plan Created on FLY | { "Status":"Sucess" } | { "Success": "Success", "TicketId": "176970430048371138801" } | Pass
Case # 7_2 | Pushing Inventory & Rates | Invalid Date Value | Date must be current or future within 500 days range | Place Valid Hotel Id, Room Type Id, Rate Plan Id and Dates | Invalid Date Range | { "Errors": [{ "Code": "925", "ShortText": "from date has passed (2020-08-30)" }], "Status": "Fail" } | {"Errors":[{"Code":"925","ShortText":"fromdate has passed (2020-08-30)"},{"Code":"925","ShortText":"fromdate has passed (2020-08-30)"}],"Status":"NotProcessed"} | Pass
Case # 7_3 | Pushing Inventory & Rates | Valid Hotel Id, Room Id, Rate Plan Id & Date Value | Valid Hotel Id, Room Id, Rate Plan Id & Date Value | Place Valid Hotel Id, Room Type Id, Rate Plan Id and Dates | Success | { "Status": "Sucess" } | { "Success": "Success", "TicketId": "176970431008347346566" } | Pass
Case # 7_4 | Pushing Inventory & Rates (Multiple Requests) | Valid Hotel Id, Room Id, Rate Plan Id & Date Value | Valid Hotel Id, Room Id, Rate Plan Id & Date Value | Place Valid Hotel Id, Room Type Id, Rate Plan Id and Dates | Success | { "Status": "Sucess" } | { "Success": "Success", "TicketId": "176970431242772731894" } | Pass
Module Name | Reservation / Booking
Analysed By
Date of Analyse
Please Note:
for reservation json, we will be passing along the details to PMS in reservation as received from OTA channel.
If information is not allocated from channel, we will be passing empty node.
System on your side must be flexible enough to let the empty node parse through.